## Slide 1: Business Continuity Disaster Recovery Test Briefings
August 18, 2021

## Slide 2: AGENDA
TESTING GOALS AND OBJECTIVES
REVIEW OF TESTING PROTOCOL
BUSINESS CONTINUITY TESTING
PARTICIPATING MARKETS
OPEN DISCUSSION
RELEVANT LINKS
REMAINING SCHEDULE

## Slide 3: INTRODUCTION
Canadian Derivatives Clearing Corporation Paul Barbara | ICE Clear Credit Saurabh Mittal
Cboe Futures Exchange Cole Chmielewski | Minneapolis Grain Exchange Ben Lundgren
Cboe SEF Adam Loeffler | Montreal Exchange Jean-François Royal, André Ionescu
CME Group Don Moore | Nodal Exchange / Nodal Clear Stefan Misterek
Eurex Wolfgang Deiseroth | Options Clearing Corporation Diego Cuevas, John Kobos, Karen Glad
Euronext Daniel Cousin | Small Exchange John Hever
ICE Exchange / ICE Clear - ICUS, ICEU, ICSG, ICE Trade Vault / eConfirm Several ICE representatives | Traiana Limit Hub Ash Vincken

## Slide 4: I. TESTING GOALS AND OBJECTIVES
The FIA Disaster Recovery Test will take place on Saturday, October 23rd, 2021
We will test the ability to conduct critical business functions (order entry through clearing) from alternate/back-up facilities simultaneously
We will test disaster recovery capabilities among futures commission merchants, back-office service providers, recovery services providers, and trading system vendors
We will test the connectivity between exchanges, clearinghouses and their constituents’ back-up facilities, a ”back-up to back-up” test, and confirm member firms’ ability to send and receive information to and from their back-up facilities and interfaces

## Slide 5: TESTING GOALS AND OBJECTIVES (Cont’d)
We will test end-to-end processing by exchanges through to, and including clearing houses; process actual test trades and produce test end of day reports with the test data
We will enter a small but meaningful sampling of orders and trades which will be carried out by a limited number of essential personnel from recovery sites or alternate work locations
We will confirm the receipt/transmission of information to and from clearing members
We will transmit key clearing reports and information to clearing firms to verify “round-trip” communications

## Slide 6: II. REVIEW OF TESTING PROTOCOL
Exchanges will specify products available for order entry/trading
All exchanges will use their electronic trading venues for the test and will process test data through to end-of-day reports for clearing members. Testing will take place between 9:00 AM and 3:00 PM EDT, unless otherwise specified.
The FIA will coordinate the test via an open conference bridge, that will remain open for the duration of the test.
Member firms will confirm connectivity with their respective exchanges/clearinghouses:
  Pre-test connectivity testing will be offered, as applicable

## Slide 7: REVIEW OF TESTING PROTOCOL (Cont’d)
Unless noted, firms will execute a pre-defined script of orders, and firms will use test accounts.
Exchanges will generate fill reports on the orders
All firms will report results and confirm post-test production connectivity to their respective exchanges
Test plans will be distributed by the exchanges and will also be available on the FIA website at: https://www.fia.org/events/2021-fia-disaster-recovery-exercise

## Slide 8: III. BUSINESS CONTINUITY TESTING
All participants are encouraged to use the test date to exercise their business continuity capabilities
Firms, vendors, exchanges, clearing houses and swap execution facilities should manage the test, enter orders and have staff work from their alternate work sites
Business continuity plans should be reviewed; those personnel that would be required to either report to an alternate work site – or work remotely from home– should do so.
As part of the registration process, firms will be asked if they plan to have staff work remotely and from what city locations.

## Slide 9: IV. PARTICIPATING MARKETS
2021 FIA DR TEST

## Slide 10: CBOE FUTURES EXCHANGE
Will allow for connectivity in primary site starting at 7:00 AM CT with failover to secondary site occurring at or before 7:30 AM CT.
Following failover the remainder of the test will use the secondary site at 350 Cermak in Chicago. Firms must target secondary IPs to access ports in 350 Cermak.
The session will open at 7:30 AM CT or as soon as the failover to the secondary site is complete.
Participants are encouraged to enter orders and trade with other participants. Firms are also encouraged to test Web-based applications such as Risk Management and Block/ECRP trade entry.
Required Participants that were notified of their obligation to participate in the FIA test back in June must perform at least two trades in the secondary site to satisfy the testing requirement.
Order entry systems will reflect October 23rd trade date.
Test Script is available on the CFE website.

## Slide 11: CBOE FUTURES EXCHANGE (Cont’d)
Secondary site ports in Chicago are available for telnet testing at any time. Session level connectivity testing (login/heartbeating) available during regular trading hours and on Saturday, September 25th and on Saturday, October 2nd.
Contact Cboe NOC with any connectivity related questions: 913-815-7005.
Albert Jimenez and Cole Chmielewski contact info:
913.815.7069, ajimenez@cboe.com
913.815.7253, cchmielewski@cboe.com

## Slide 12: CBOE SEF
Will use secondary site at LD4 in London. Firms must target secondary IPs to access ports at LD4.
The trading session will be open from 9:00 AM to 11:00 AM ET.
Participants are encouraged to enter orders and trade with other participants.
Customers who would like to participate are required to submit notice to Cboe SEF thirty (30) days in advance of the scheduled test and engage in the Connectivity Test weekend on Saturday September 25, 2021.

## Slide 13: CBOE SEF (Cont’d)
Test Script
Customers with connectivity to the secondary site will be allowed to connect, submit orders, and receive market data for the duration of the test. The trade date for all transactions on all SEF messaging (e.g. order acknowledgements, execution reports, drop, and market data) during this test will be the following Monday (10/25/2021). The following functionality will be available during the DR test:
  Order entry
  Trade matching
  Market data dissemination
  FIX Drop copies
Customers will be able to use their Production logins to connect and trade during the BCP/DR test.
Contact info:
212.378.8558
fxtradedesk@cboe.com

## Slide 14: CME GROUP
CME Group test window will run from 9am to 1pm EDT
The primary Chicago data center houses all CME Group production applications, CME Globex, and Clearing as well as Co-location services. The out-of-region data center houses Disaster Recovery (DR) services and will be accessible according to the failure scenarios highlighted in the following 2 scenarios. Please note that the CME Group utilizes a Single IP for firms’ connectivity to MQ and a Single DNS name (sftpng.cmegroup.com) for firms’ connectivity to sFTP for production and DR environments.
This two-scenario approach highlights the potential scenarios that could impact customer connectivity during a disaster in Chicago. In both scenarios Clearing and Globex will be available via the disaster recovery facility.
Test Scope

## Slide 15: CME GROUP (Cont’d)
Scenario 1: In Region: Chicago Metropolitan Disaster:
The primary CME Group data center and redundant access node have been forced to cease operations. All applications will begin functioning in the CME Group out-of-region data center and all Chicago-based connectivity solutions, including GLink and LNET, are inoperable. Customer connectivity that is not dependent on Chicago data centers will be maintained; there will be no changes required by these customers.
Note: GLink and LNET are out of scope in this first scenario, firms that are dependent on Chicago data centers submitting test trades during this window would need to utilize their back-up order routing facilities. This scenario will run for approximately the first (1) hour of the CME Group test window (9am to 10 am EDT)

## Slide 16: CME GROUP (Cont’d)
Scenario 2: In Region: Primary Data Center Production Room Failure, Co-location Services Available
During this scenario only the applications and production environments are disabled in the primary data center. All applications will continue functioning in the CME Group out-of-region data center. This scenario also assumes that all carrier and network facilities at the CME Group redundant access node as well as CME Group Co-Location facilities are not impacted by the failure. All methods of customer connectivity will be maintained, GLink and LNET have been recovered, and there will be no changes required by the customer. Customers will continue to connect to CME Globex and Clearing applications via production IP addresses.
Note: Glink/LNET have been recovered. Customers will continue to connect to CME Globex and Clearing applications via production IP addresses. LNET has been restored, firms utilizing LNET can test MQ connectivity for the duration of the test. This scenario is scheduled to run for the duration of the CME Group test window (10am to 1pm EDT).
  Single IP address/Production IP address for MQ
  Single DNS name for firms connectivity to sFTP
  There will not be any Open Outcry testing

## Slide 17: CME GROUP (Cont’d)
Test Preparation
Ping testing will be held on Aug 28th & Sept 18th from 8:00 a.m. to 1:00 p.m. EDT.
Firms must register via the FIA website
Contact CME Clearing Support (CCS) team at (312) 207-2525 with any questions on MQ IP addresses (same as Prod IP’s) or DNS name for sFTP connectivity
General questions may be directed to the Business Continuity Team - BCM@cmegroup.com

## Slide 18: CME GROUP (Cont’d)
Support During the Exercise
Members should contact their designated CME customer representative (will be assigned), or Clearing Support Team (312) 207-2525 to report any issues.
Members should contact the GLOBEX Control Center at the GCC Hotline numbers which are: U.S. at +1 800 438 8616, in Europe at +44 800 898 013 or in Asia at +65 6532 5010 to report any trading problems encountered throughout the test

## Slide 19: CME GROUP (Cont’d)
Test Execution – Globex
a) Verify firm connectivity:
  Clearing DR test window scheduled to begin at 9:00 AM EDT
  Any trades done prior to the start of the test will not be captured.
  October 22nd is the valid order entry date
  All fills will be sent back to the Firms with the trade date of October 22nd.
  Firms can send a test order in any market
b) Order entry via test script as follows:
  Enter a total of 10 trades.
  Firms should send orders that will be listed on GLOBEX for the test.
  Firms may receive crossed trades and/or trades with other counterparties.

## Slide 20: CME GROUP (Cont’d)
Test Execution - Clearing
Clearing – 9:00 AM EDT
  a) Trade reporting to firms’ back office systems:
  - Firms will verify receipt and delete them.
  b) Connect to CME’s sFTP server, using the Production DNS Name:
  1) Using Friday’s data, FTP the PCS and Large Trader reports.
  - CME staff will verify receipt and delete them.
  2) CME will transmit Thursday’s Trade Register and SPAN files.
  - Firms will verify receipt of these files and delete them.
  3) If applicable, enter a block trade for 5000 EDH2 @99.810
  - CME staff will verify receipt of the block trades and delete them.

## Slide 21: CME GROUP (Cont’d)
At the Conclusion of the Exercise
Delete any testing files
Fail back to your Production environment
Upon test completion firms should contact the GCC at the GCC Hotline numbers which are: U.S. at +1 800 438 8616, in Europe at +44 800 898 013 or in Asia at +65 6532 5010 acknowledging test completion, and then complete/submit the test questionnaire posted on the FIA website to recap the test results. No firm names will be used on the recap report

## Slide 22: EUREX
  Scenario/Implications
  The DR test scenario will simulate a partial outage of the primary data center facility (the co-location facility will remain up and running)
  The simulation back-end (located in a different data center) will be used to serve as the DR production back-end.
  T7 interfaces located in the primary data center will switch to the simulation infrastructure and will need to be accessed via simulation network addresses (please check “T7 Disaster Recovery Concept 2021 – update” for details).

## Slide 23: EUREX (Cont’d)
Available Interfaces
The following T7 interfaces will be available during the DR test exercise:
Enhanced Transaction Solution (ETI)
New FIX LF interface (introduced with T7 Release 9.0)
T7 GUI
T7 Market Data Service (MDI)
T7 Enhanced Market Data Service (EMDI)
T7 Enhanced Order Book Interface (EOBI)
Reference Data Interface (RDI)
Common Report Engine (CRE)

## Slide 24: EUREX (Cont’d)
Test Execution
Customers participating in the DR test exercise can
receive market data via MDI, EMDI, EOBI and T7 GUI
read reference data via RDI
receive Reference Data File (RDF) via CRE
enter orders and quotes via ETI and T7 GUI

## Slide 25: EUREX (Cont’d)
Test Execution (cont’d)
Production reference data will be used, including User IDs, T7 GUI keys and ETI sessions.
Please note: Changes done during the test exercise will NOT be copied back to production after the test. It is not advised to perform any changes to this data during the test exercise!

## Slide 26: EUREX (Cont’d)
Success criteria for the DR test exercise
The DR test exercise can be regarded as successful when
either a message “Connection Test ##### <hh:mm:ss>” appears with an increasing sequence number in the market news view (news board) of the T7 Trader or Admin GUI
or a successful session or trader login via ETI has been performed and MDI/EMDI/EOBI/RDI heartbeats have been received.

## Slide 27: EUREX (Cont’d)
Timeline on 23 October 2021
Start of DR scenario test 14:00 CET
End of DR scenario test 16:00 CET
Start of prod environment re-connect test 17:00 CET
End of prod environment re-connect test 18:00 CET
Primary Contact
Technical Key Account Manager (via individual VIP number)
Detailed information
Eurex Circular 078/2021
Updated version of “T7 Disaster Recovery Concept 2021” - Accessible end of August under the following path:
Eurex.com > Support > Initiatives & Releases > T7 Release 9.1 > Network Access

## Slide 28: EURONEXT
MAIN PRINCIPLES OF THE TEST
Euronext will simulate a failover of DC1 to DC2 during the continuous trading session and will manage the transfer through the appropriate decision-making process (for Cash & Derivatives Markets).
As soon as Euronext considers DC2 to be fully operational for Cash & Derivatives markets, a pre-opening session and a trading session will be set up on Optiq Cash & Derivatives, and customers will be given by our readiness status to reconnect.
Customers are responsible for making sure that their internal systems and access means are correctly synchronised with Euronext central systems.

## Slide 29: EURONEXT (Cont’d)
The following are included in the test:
Both production trading systems of Euronext’s Data Centres: DC1, located at Basildon (UK) and DC2 (DR Data Centre), located in the Paris region.
Trading engines:
  Optiq Cash Markets: Equities, Funds, Warrants & Certificates, Fixed Income, Trade Confirmation System (TCS), Transaction Reporting and Publication System (Saturn) and Index platform
  Optiq Derivatives Markets: Equity Derivatives, Index Derivatives, Commodities.
Related access means: Optiq Cash & Derivatives Order Entry available via OEG Market Data: All MDG market data services
The following systems/ services are not part of the test:
Co-location access means
Post-trade systems: trades will not be integrated in the clearing system and no clearing members will be involved in this test.
SCOPE OF THE TEST

## Slide 30: EURONEXT (Cont’d)
DR TEST SCHEDULE FOR CASH & DERIVATIVES MARKETS
Note: All timings are approximate and are stated as CET
10:30 Beginning of the test. Participants are invited to check the status and timeline on the Market Status web page
11:30 Pre-opening phase (Core call) on DC1 (Customers can connect and send orders)
11:45 Opening phase (Core call) on DC1 (Customers can send orders and trade)
13:00 Beginning of the failover from DC1 to DC2 (Order Entry access means disconnected from the markets)
15:00 Beginning of the failover from DC1 to DC2
16:30 End of the test

## Slide 31: EURONEXT (Cont’d)
CUSTOMER PARTICIPATION
Euronext strongly encourages any customers to participate actively in this test in order to ensure that they are familiar with the Euronext failover process.
As a reminder, the registration is available here to participate to the test: https://connect2.euronext.com/en/form/euronext-disaster-recovery-test
COMMUNICATION
During the test Euronext will keep customers informed through the Live Market Status web page: www.euronext.com/market-status

## Slide 32: ICE EXCHANGE
The ICE Exchange secondary site in Atlanta will be used for the FIA DR Test on Saturday, October 23rd
The following markets/products will be available for testing:
  ICE Futures US Sugar 11
  ICE Futures US Dollar Index
  ICE Futures US Canola
  ICE Futures Europe WTI
  ICE Futures Europe Three Month Euribor
  ICE Futures Singapore Mini Brent
Test markets will follow the schedule below (all times in EDT)
  0001 PRE-OPEN
  0900 OPEN
  1200 CLOSE
Interface availability:
  All front-end trading interfaces (WebICE, ICE Block, FIX, Pricefeed)
  All reporting interfaces (Deal Reports, Position Reports, etc.) will be accurate based on test (and live SPOT/OTC/NGX) trading activity
  Back-office interfaces NOT available (Credit Management, Clearing Admin, etc.)
IMPORTANT NOTE:
All Spot, OTC, and NGX markets will be open and live throughout the testing. NO testing is permitted in these markets. Any trades entered in these markets are valid trades and will be honored as such.

## Slide 33: ICE EXCHANGE (Cont’d)
Registration and user setup
Registration for the ICE Exchange is not required
All existing customers with valid trading IDs are welcome to participate
Existing production User ID and password will be used for login
No test/temporary IDs or access will be provisioned for the FIA DR testing
Test administration and support
All participants MUST clean up all backend system data after testing
No futures trades performed during testing hours will be valid
At the end of the DR testing period, all futures trade data will be deleted from the ICE Exchange and databases and no record of those test transactions will persist
The ICE Helpdesk (770-738-2101 Option 1) will be available 0800-1300 ET
No network, DNS, or IP changes will be required to connect to the ICE Exchange secondary site during the ping test or the FIA DR Test
IMPORTANT NOTE:
All Spot, OTC, and NGX markets will be open and live throughout the testing. NO testing is permitted in these markets. Any trades entered in these markets are valid trades and will be honored as such.

## Slide 34: ICE EXCHANGE (Cont’d)
Clearing Information
All ICE Futures US trades will be submitted to the ICE Clear US secondary site
All ICE Futures Europe trades will be submitted to the ICE Clear Europe secondary site
All ICE Futures Singapore trades will be submitted to the ICE Clear Singapore secondary site
Ping test overview
Atlanta DR site will be available for Ping Pre-Test on Saturday, September 11th
All futures markets will be closed, only ping and system logins will be permitted
Spot/OTC/NGX markets will be open for production trading – no test trades permitted
The system will be available for testing between 0900-1200 ET
The ICE Helpdesk (770-738-2101 Option 1) will be available between 0900-1200 EDT
No network, DNS, or IP changes will be required to connect to the DR site during the ping test or the FIA DR Test
IMPORTANT NOTE:
All Spot, OTC, and NGX markets will be open and live throughout the testing. NO testing is permitted in these markets. Any trades entered in these markets are valid trades and will be honored as such.

## Slide 35: ICE CLEAR ICUS, ICEU, ICSG
ICE operates several Clearing Houses (CHs) globally, each of which will participate in the annual FIA Industry Disaster Recovery testing. The ICE CHs covered within this section are:
ICE Clear US (ICUS) ICE Clear Europe (ICEU)
ICE Clear Singapore (ICSG)
All CMs must register via the FIA registration website
Trade date will be Saturday, October 23rd. Clearing date will be Monday, October 25th.
Clearing members will use production URLs for the following clearing applications. URLs by CH are listed below.
- MFT - ECS - FEC
Trade messaging MQ changes will be completed prior to the start of the test.

## Slide 36: ICE CLEARING HOUSES (Cont’d)
Ping Testing
Clearing members must verify connection to online clearing applications, using production URL’s and MQ configurations.
Ping testing will be conducted on Saturday, September 11th from 9am-12 pm ET. While this is primarily an opportunity to verify changes necessary for trade messaging over MQ, the clearing applications available online will also be switched over.
For MQ, Clearing members must verify connection by sending an MQ ping through their channel.

## Slide 37: ICE CLEARING HOUSES (Cont’d)
Test Day
All times Eastern Time (ET).
Clearing applications will be available at 9:00 am on Saturday, October 23rd.
Beginning at 12:30 pm, ICE will revert all trading and clearing applications, including MQ channels, back to production.
An advisory will be sent to test participants and announced on the ICE and FIA bridge calls.
Clearing members are strongly encouraged to confirm their reconnection to production at the conclusion of the testing.

## Slide 38: ICE CLEARING HOUSES (Cont’d)
Test Cases – Test Day
  Clearing members will log in to post trade management systems (ICE FEC) to allocate test trades which have passed through to clearing from the WebICE trading system.
  Clearing Members will confirm receipt of trade messages over MQ.
  Clearing Members will log in to ECS to verify connectivity. CMs may enter test banking instructions in ECS (instructions will not be passed to SWIFT).
  Clearing Members will login to MFT to deliver a test GCM, FIFO or Large Trader file (GCM, FIFO, or LTR for ICUS) and retrieve a Matchoff file and Clearing reports.
CM’s are required to complete and submit the checklist of results to each clearing house at the completion of the testing.

## Slide 39: ICE CLEARING HOUSES (Cont’d)
ICE Clear US
ECS (https://ecs.usclearing.theice.com/console/index.html)
MFT (mft.usclearing.theice.com)
FEC (https://fec.usclearing.theice.com/)
ICE Clear Europe
ECS (https://ecs.euclearing.theice.com/console/index.html)
MFT (mft.euclearing.theice.com)
FEC (https://fec.euclearing.theice.com/)

## Slide 40: ICE CLEARING HOUSES (Cont’d)
ICE Clear Singapore
ECS (https://ecs.sgclearing.theice.com/console/index.html)
MFT (mft.sgclearing.theice.com)
FEC (https://fec.sgclearing.theice.com)

## Slide 41: ICE TRADE VAULT/eCONFIRM
ICE Trade Vault/eConfirm will participate in the industry wide testing on October 23rd 2021. During this testing window (9am – 11am ET) the following systems will be failed over to our disaster recovery site for testing.
ICE eConfirm
Trade Vault US
Trade Vault Canada
Trade Vault EMIR
Trade Vault Remit
MFT (Secure FTP Server)
No changes to URL’s/DNS’ are required for testing.
  www.icetradevault.com
  mft.tradevault.theice.com
No REMIT data will be sent to ACER during testing
IMPORTANT NOTE:
Any trades entered during the testing window are NOT valid trades and will NOT be ported
back to our Production environment.

## Slide 42: ICE TRADE VAULT/eCONFIRM (Cont’d)
Registration and user setup
  Registration for ICE Trade Vault/eConfirm is not required, but is recommended.
  Contact tradevaultsupport@theice.com if you plan to participate.
  All existing customers with valid Trade Vault/eConfirm IDs are welcome to participate
  Existing production User ID and password will be used for login
  No test/temporary IDs or access will be provisioned for the FIA DR test.
Test administration and support
  At the end of the DR testing period, all data from the testing period will be deleted from ICE Trade Vault and eConfirm databases and no record of those test transactions will persist.
  No network, DNS, or IP changes will be required to connect to the ICE Trade Vault/eConfirm secondary site
  Starting @ 11:15 ET all systems will be reverted back to production.
  Notifications will be sent when systems are in TEST mode and when systems are back in PRODUCTION mode.
  Support will be available from 0900-1200 ET by contacting the helpdesk line @ 770-738-2101 Option #4
IMPORTANT NOTE:
Any trades entered during the testing window are NOT valid trades and will NOT be ported
back to our Production environment.

## Slide 43: ICE TRADE VAULT/eCONFIRM (Cont’d)
Test Cases – Recommended
  The recommended test cases have been outlined in a separate document. Please contact the sales team (tradevaultsupport@theice.com) if you are planning to participate and they will provide those recommended test cases.
Ping Test: September 11th 2021
  ICE Trade Vault /eConfirm will participate in the first ping test date. On this day clients will be able to test their access to the following applications.
    Trade Vault US
    Trade Vault Canada
    Trade Vault Remit
    Trade Vault EMIR
    MFT (SFTP) Server
IMPORTANT NOTE:
Any trades entered during the testing window are NOT valid trades and will NOT be ported
back to our Production environment.

## Slide 44: ICE CLEAR CREDIT
ICE Clear Credit will participate in the FIA Disaster Recovery Test on Saturday, October 23rd.
All times are Eastern Time (ET).
CDS clearing applications will be available at 9:00 am ET.
Beginning at 11:00 am ET, ICE will revert all clearing applications back to production.
Ping Testing
Ping testing will be conducted on Saturday, September 11th from 9:00 am ET -11:00 am ET. The CDS clearing applications available will be switched over. Participants must verify connection to the CDS clearing applications using the URLs given in the following slides.

## Slide 45: ICE CLEAR CREDIT (Cont’d)
The following CDS clearing applications will be available through the ICE Clear Credit DR site for Clearing Participants to test:
Managed File Transfer (MFT):
  File Upload
    E.g. Clearing Eligible Trade File
  File Download
    E.g. Clearing Eligible Trade File, Final Clearing Instruction File
ECS Banking System
Direct Pricing:
  FIX Pricing API
  PACE UI
ICE Risk API
*ICE Clear Credit will be operating from its DR location; therefore all data entered into the DR clearing system will be deleted. CDS Clearing Participants that receive data during the test to their production system should take precautions not to process disaster recovery transactions with production data.

## Slide 46: ICE CLEAR CREDIT (Cont’d)
MFT – Retrieve Data Files via SFTP CDS Clearing Participants can test the SFTP functionality in order to retrieve data files. ICE Clear Credit will make production data files available to CDS Clearing Participants by using the below:
MFT URL for Individual Users: securemft.icc.theice.com IP Address: 63.247.112.89 Port: 22
MFT URL for Service Account Users: mft.icc.theice.com IP Address: 63.247.112.88 Port: 22

## Slide 47: ICE CLEAR CREDIT (Cont’d)
ECS Banking System
ICE Clear Credit CDS Clearing Participants should make sure they have access to the ECS Banking system. Clearing Participants should login to the below URL to ensure they have access:
ECS URL: https://ecs.icc.theice.com/trade/Login

## Slide 48: ICE CLEAR CREDIT (Cont’d)
Direct Pricing ICE Clear Credit CDS Clearing Participants should make sure they have access to the FIX Pricing API and PACE UI. Clearing Participants should login to ensure they are able to establish connectivity to these applications.
FIX Pricing API
FIX URL: fix.icc.theice.com IP Address: 63.247.112.95 Port: 10001
PACE UI
PACE UI URL: https://pace.theice.com

## Slide 49: ICE CLEAR CREDIT (Cont’d)
At the Start of the Test
Participants are encouraged to contact the ICE Clear Credit CSS staff at (312) 836-6890 prior to the DR test. This will allow the appropriate ICE Clear Credit CSS staff to monitor results and assist participants in the DR test if need be.
At the Completion of the Test
Once a Clearing Participant has determined that all their test objectives have been met, please send an email outlining each item tested along with the results to css@theice.com.
At the completion of the test, Clearing Participants are encouraged to contact CSS at (312) 836-6890 in order to provide ICE Clear Credit with your firm’s CDS DR test status.

## Slide 50: ICE CLEAR CREDIT (Cont’d)
How to Participate
ICE Clear Credit CDS Marketplace Disaster Recovery Test Request Form To help prepare for a smooth CDS Marketplace disaster recovery test, please complete the following form and provide appropriate contacts. After completion, please return the form by email to css@theice.com. Will your firm be participating in the ICE Clear Credit Disaster Recovery Test?
Yes ____ No ____ SCM ____ FCM ____
Firm Name | 
 | Contact | Position | Phone | DR Phone
Primary |  |  |  | 
Secondary |  |  |  | 

## Slide 51: ICE CLEAR CREDIT (Cont’d)
Contacts
Should you have any questions, please call or e-mail the Client Services and Support Group:
Client Services and Support 312-836-6890 css@theice.com

## Slide 52: MINNEAPOLIS GRAIN EXCHANGE
MGEX will be utilizing MGEX DR systems for the FIA DR test on Saturday, October 23rd.
Clearing Members and Firms must register on the FIA website to participate in the MGEX Clearing test.
Testing will occur from 8AM – Noon CDT on October 23rd.
Trade date can be either October 22nd or 23rd.
All MGEX products will be available for testing.
Trade Entry via CME Globex® and MGEX Trade Entry Matching System (“TEMS”)
MGEX Open Outcry trades will be entered in the TEMS system.
Trades entered for MGEX products into the CME GLOBEX platform and MGEX TEMS will be cleared by MGEX Clearing using the MGEX DR Site.

## Slide 53: MINNEAPOLIS GRAIN EXCHANGE (Cont’d)
After Trade Entry is completed, trade files (TREX files) will be generated by the MGEX DR Clearing Server and placed on the MGEX DR FTP server. The MGEX DR FTP server is accessible via IP with the same logins and passwords as the production system.
Participants are reminded to fail back to Production systems at the conclusion of the FIA DR test.
Connectivity and Ping testing required on either 9/11 or 9/25, or can be scheduled on an ad-hoc basis.
Firms having technical issues with MGEX Clearing on the day of the test may call the MGEX Clearing group at (800) 827-4746 (option 3 then option 1) or (612) 321-7146 for support.
Please contact MGEX Clearing group for information or support pertaining to the FIA DR Test. Email: clearing@mgex.com

## Slide 54: TMX GROUP MONTREAL EXCHANGE
MX will offer two connection periods. An early one that will permit connectivity to the primary site, and a second to access our back-up site.​
Times and systems availability will be as follows:
*System will be up by 11:00
Time | Access to Primary or back-up system |  | Instrument state
7:00 AM – 8:20 AM | Primary |  | Pre-open
8:20 AM – 8:45 AM |  |  | Markets open
8:45 AM – 11:00 AM* | No access | 8:45 – 9:00 disaster simulation | Market out of service
 |  | 9:00 – 11:00 recovery | 15 minutes – Pre-Open
11:00 AM* - 1:30 PM | Back-up |  | Markets open

## Slide 55: MONTREAL EXCHANGE (Cont’d)
No network, DNS, or IP changes will be required to connect to the DR site during the connectivity test or the FIA DR Test
No trades will occur during the Pre-Opening period
MX will provide automated market volume for bid/offer on selected instruments in the back-up environment
Orders must be entered with an October 23rd Trade Date (day orders only)
Broadcast of trades transmitted to firms via SOLA Trading protocols and disseminated via the HSVF & OBF market data feeds
No trades performed during testing hours will be valid
All participants MUST clean up all backend system data after testing

## Slide 56: CANADIAN DERIVATIVES CLEARING CORPORATION
Similarly to MX, CDCC will also offer two connectivity periods; the first at the primary site, and the second at the DR site.
  Clearing Members will verify connectivity and can send/receive messages
  No network, DNS, or IP changes will be required to connect to the DR site during the connectivity test or the FIA DR Test
  Clearing Members must register via the FIA website
  Clearing Members will test SFTP/Reporting capabilities
  Clearing Members will test FIXML capabilities
  Clearing Members will test PCS functionality
On October 23rd test day only, provided there are no issues or delays, markets will be in Pre-Opening state by (latest) 11:00 AM EDT
  No trades will occur during the Pre-Opening period
  Pre-Opening and Opening Times will need to be confirmed (dependent on actual recovery time)
  MX will provide automated market volume for bid/offer on selected instruments
Provided there are no issues or delays, the market will open at 11:15 AM EDT
  No trades performed during testing hours will be valid
  All Clearing Members MUST clean up all backend system data after testing
  Trades will flow from MX to CDCC’s environment
  Trades & Positions will be available for validation via SOLA® Clearing Manager

## Slide 57: MX/CDCC (cont’d)
Important Dates
Connectivity testing will be offered on September 11th, 2021 for both MX and CDCC participants/clearing members
Contacts
Contact the following for Montreal Exchange business questions:
Contact Paul Barbara with any CDCC business questions:
514-787-6549
CDCC-CS@tmx.com
André Ionescu | Jean-François Royal
514-787-6624 | 514-787-6568
andre.ionescu@tmx.com | jean-francois.royal@tmx.com

## Slide 58: NODAL EXCHANGE / NODAL CLEAR
We will failover to the DR site
We will change DNS to point at our DR site
  IPs will change
  DNS names will remain the same
Pre-test requirement - Users must register via the FIA website
Participants will use logins on production accounts (Nodal Platform, Trading frontends)
All platform activity will be removed after the test
Trading date will be October 22nd (TBC)
Connectivity testing will be on an ad-hoc basis during September for those signed up via the FIA website (If applicable)

## Slide 59: NODAL EXCHANGE (Cont’d)
Web and SFTP will be accessible
We will not send emails
We will publish a schedule to registered participants
For support please call 703-962-9860 or email helpdesk@nodalexchange.com

## Slide 60: OPTIONS CLEARING CORPORATION
Overview
OCC’s version of the FIA Business Continuity and Disaster Recovery Industry Test will include round trip processing with members and exchanges. Ping testing will only be supported on 7/24/21 and 10/2/21.
Similar to prior year’s testing, OCC will simulate a standard business day from market open through positions finalization.
OCC will support all inbound and outbound communication protocols from our DR environment along with the ENCORE GUI application.
All data received will be processed and distributed to registered participants according to their registration specifications.

## Slide 61: OPTIONS CLEARING CORPORATION (Cont’d)
Test Objectives
Test round trip processing with Members and Exchanges including trades, post trades, positions finalization, outbound data distribution and end of day reports
Test the ability to conduct critical business functions (trades processing through positions finalization) from alternate/back-up/DR facilities simultaneously

## Slide 62: OPTIONS CLEARING CORPORATION (Cont’d)
Test Details
Starting Inventory
  Product/Contract and Position Inventory for the test will be a snapshot of the production inventory as of “Market Open” Thursday, October 21, 2021
Symbols / CUSIP
  OCC will support production symbols and CUSIP’s
Trade Date
  Trade date for the OCC Encore System will be Thursday, October 21, 2021
  All inbound Exchange Trades will have a trade date of Saturday, October 23, 2021
  Inbound Member transactions will be accepted with a trade date of Thursday, October 21, 2021 or Saturday, October 23, 2021.
  Exchange Trades and Member Post Trade data received with a trade date of Saturday, October 23, 2021 will be flipped to Thursday, October 23, 2021 for processing.
  All outbound data from OCC will have a trade date of Thursday, October 23, 2021.

## Slide 63: OPTIONS CLEARING CORPORATION (Cont’d)
General Test Information
Description | Details
Test Registration Required | Yes for Non-Mandated Participants Registration only accepted via OCC website: https://www.theocc.com/clearing/certification-testing/reg_sci_dr_industry_test_registration.jsp OCC Registration Ended July 31, 2021, but will work with firms who late register on a best efforts basis
Environment Used For Test | DR Environment
Advanced Planning & IT/Connectivity Contacts | occDRtest@theocc.com Member Services Help Desk 800-621-6072
Test Day Contacts | Member Services Help Desk 800-621-6072 Option 1 Support will be available for the duration of the test
Availability of Test Day Conference Bridge | No – OCC will distribute broadcast emails throughout the test
Completion of Test Acknowledgement Protocol | Complete Email Template and Send To occDRtest@theocc.com

## Slide 64: OPTIONS CLEARING CORPORATION (Cont’d)
Description | Details
Systems Supported | Encore, DDS
Client Connectivity | IP and Leased Lines (includes NDM, SFTP, MQ)
Production Systems Reset and Test Data Purged | Yes, - Prior to Monday opening Firms are responsible for purging test data on their systems
Special Registration Requirements | Advanced Registration Required – No Day of Registration Accepted
Special Instructions | OCC will require all firms testing on October 23, 2021 to pre-test connectivity on one of the designated test dates in July or October (7/24 or 10/2)
General Test Information (Cont’d)

## Slide 65: OPTIONS CLEARING CORPORATION (Cont’d)
Participants must register in advance via the OCC website
Once registered OCC will contact registered participants to provide overview of testing scope and distribute the Industry Test Questionnaire and the 2021 Technical Specification forms which must be filled out and returned to OCC.
Members can choose to test from Production/Back-up or DR site and must disclose to OCC what site is being used for the test
Connectivity Testing is required in advance of participation in the Industry Test. OCC will support connectivity testing on the following dates.
Testing Pre-Requisites
Day/Date | Time (ET) | Connectivity Pre-registration | 2021 Tech Spec Form
Saturday, Oct 2, 2021 | 9:00 a.m. – 3:00 p.m. | Required | Required

## Slide 66: OPTIONS CLEARING CORPORATION (Cont’d)
Business/ Trade Date | Time (ET) | Activity | Inputs/ Outputs | Description
Thursday 10/21/21 / Saturday 10/23/21 | 8:15 a.m. – 8:45 a.m. | Pre-Market Open Connectivity – Exchange Only | N/A | Resolution of connectivity & start-up issues
 | 8:45 a.m. – 9:15 a.m. | Pre-Market Open Connectivity - Participants | N/A | Resolution of connectivity & start-up issues
 | 9:30 a.m. – 12:00 p.m. | Mock Trading Cycle Post Trade Cycle | Inputs Outputs | Real-time Trades (Exchanges) Trade Balancing (Exchanges) Backup Batch Trade Files (Exchanges) Real-time FIXML, Post Trades (Members) Batch FIXML Post Trades (Members) External Encore Post Trades (Members) Real-time Trade DDS – Pends/Rejects (Exchanges) Real-time DDS (Members)
 | 12:00 p.m. | Market Close - Exchange Checkpoint |  | 
 | 12:00 p.m. – 4:00 p.m. | Positions Finalization / End of Day | Inputs Outputs | N/A ORSA DDS (Exchanges) Batch DDS (Members) External Encore Reports (Members) Position Activity Position Summary

## Slide 67: SMALL EXCHANGE
Overview
The Small Exchange will test its ability to conduct business from its disaster recovery (DR) facility.
Pre-test Requirement
Prior to the DR test on October 23rd, the Small Exchange will host mandatory pre-test connectivity tests. The Small Exchange pre-test dates are August 28th, September 11th and September 25th from 9:00 AM to 12:00 PM CT.
Test Schedule
The expected test schedule on October 23rd will be as follows (times in Central Time):
8:00 AM: Connectivity to Small Exchange is available
9:00 AM: Pre-open
9:30 AM: Mock trading session begins
12:00 PM: Mock trading session closes

## Slide 68: SMALL EXCHANGE (Cont’d)
Test Activity
All production symbols will be available for order entry during this mock trading session. Test participants who have completed pre-testing will be allowed to connect, submit orders, and receive market data for the duration of the test. The trade date for all transactions on all exchange messages will be the actual test date, October 23, 2020. The following will be tested and verified during the DR test:
  Connectivity
  Pre-Open
  Market open
  Order routing (trade activity)
  Market data dissemination
  Clearing
  Daily settlement price dissemination
Contacts
  Operations
  ops@thesmallexchange.com
  IT Operations
  it-ops@thesmallexchange.com

## Slide 69: TRAIANA LIMIT HUB
Traiana operates Limit Hub globally, which will participate in the 2021 FIA Industry Disaster Recovery testing.
The primary Limit Hub data center at NY will be forced to cease operations. Limit Hub will be functioning from the secondary data center in Chicago.
No action is required by Limit Hub participants as they connect to both primary and secondary instances via the same IP addresses.
The test scenario will take place between 9:00 AM and 12:00 PM EDT
Limit Hub participants should contact the support team at LHDRTestSupport@Traiana.com to report any issues

## Slide 70: TRAIANA LIMIT HUB (Cont’d)
Traiana switchover to DR site Quarterly and run production environment from Chicago site for a week / two weeks (meaning LH fully connected and live from DR site to all participants)
Possible test scenarios:
  Switch between Prod and DR sites - Transport Layer
Pre-test requirement:
  Participating firms must register via the FIA website and coordinate test scripts with Traiana
At the conclusion of the testing participating firms will confirm reconnection to production

## Slide 71: TRAIANA LIMIT HUB COMMUNITY
FCM | SEF
Bank of America Merrill Lynch | BGC Derivatives Markets
Barclays | Bloomberg SEF
BNP Paribas | Clear Markets North America
Citi | GFI Swaps Exchange
Credit Suisse | ICAP SEF
Deutsche Bank | ICE Swap Trade
Goldman Sachs | Javelin SEF
HSBC | MarketAxess SEF Corporation
JPMorgan Chase | TeraExchange
Morgan Stanley | TradeWeb (TW SEF)
Nomura | Tradition (Trad-X)
SG Americas | Yield Broker
UBS | 
Wells Fargo | 

## Slide 72: TRAIANA LIMIT HUB (Cont’d)
TEST COVERAGE – TRANSPORT
Will use Limit Hub Secondary Site (Traiana DR at Chicago)
Pre-test connectivity tests will be offered on an ad-hoc basis. Please contact us to schedule a date/time.
Contact Traiana Limit Hub Support with any test related questions: LHDRTestSupport@Traiana.com
FIX Heartbeat
  Prod to Traiana DR
  DR to Traiana DR
MQ Ping
  Prod to Traiana DR
  DR to Traiana DR

## Slide 73: V. OPEN DISCUSSION
Discussion with firms and exchanges as to their state of preparation and readiness:
  Back-up systems/communications links
  Order entry and routing
  Give up processing
  Clearance and settlement
  Use of third-party service providers
Issues or concerns
Other

## Slide 74: TESTING MATRIX (PT. 1)
Market | CFE | Cboe SEF | CME | EUREX | EURONEXT
Systems | Trading Platform | Secondary site at LD4 | GLOBEX, Clearing360, SFTP | T7 Trading Platform | Optiq CASH and DERIVATIVES, TCS, Saturn
Pre-Test/Ping Testing Dates | Sep 25 Oct 2 | Sep 25 | Aug 28 Sep 18 | N/A | 24/7 on generic port 45000
Successful Login from Members DR Site | Y | Y | Y | Y | Y
Trade Date | Oct 23 | Oct 25 | Oct 22 | Oct 23 | Oct 23
Receipt of 10 Order from Members Via Pre-Defined Scripts | Y | Y | Y | Y | Y
Transmit 10 Fil Reports to Members | Y |  | Y | N | Y
Receipt of PCS and Large Trader Reports from Members | N/A | N/A | Y | N | N/A
Download Previous Day Clearing Reports: Match Off, Report and SPAN Files | N |  | Y | N | Y
All Production Systems Restored, Test Data Re-Set | Y | Y | Y | Y | Y

## Slide 75: TESTING MATRIX (PT. 2)
Market | ICE | ICC | MGEX | MX/CDCC | NODAL
Systems | Web ICE, ECS, FEC, MFT Files, FIX Pricing API, PACE UI | Web ICE, ECS, FEC, MFT Files, FIX Pricing API, PACE UI | GLOBEX TEMS FTP | MX: SOLA Trading CDCC: CDCS (SOLA Clearing) | T7 Trading Platform Nodal Suite
Pre-Test/Ping Testing Dates | Sep 11 | Sep 11 | Sep 11 Sep 25 | Sep 11 | Ad Hoc
Successful Login from Members DR Site | Y | Y | Y | Y | Y
Trade Date | Oct 23 (Trade) Oct 25 (Clear) | Oct 25 | Oct 22 or Oct 23 | Oct 23 | Oct 22
Receipt of 10 Order from Members Via Pre-Defined Scripts | N | N | Y | Y | N/A
Transmit 10 Fil Reports to Members | N | N | Y | Y | N/A
Receipt of PCS and Large Trader Reports from Members | N | N | Y | Y | N/A
Download Previous Day Clearing Reports: Match Off, Report and SPAN Files | Y | Y | Y | Y | N/A
All Production Systems Restored, Test Data Re-Set | Y | Y | Y | Y | Y

## Slide 76: TESTING MATRIX (PT. 3)
Market | OCC | SMALL | TRAIANA
Systems | ENCORE DDS | Trading Platform | TBD
Pre-Test/Ping Testing Dates | Jul 24 Oct 2 | Aug 28, Sep 11, Sept 25 | Ad Hoc
Successful Login from Members DR Site | N | N/A | TBD
Trade Date | Oct 21 (Encore) Oct 23 | Oct 23 | TBD
Receipt of 10 Order from Members Via Pre-Defined Scripts | N/A | N/A | N/A
Transmit 10 Fil Reports to Members | N/A | N/A | N/A
Receipt of PCS and Large Trader Reports from Members | N/A | N/A | N/A
Download Previous Day Clearing Reports: Match Off, Report and SPAN Files | N/A | N/A | N/A
All Production Systems Restored, Test Data Re-Set | Y | N/A | TBD

## Slide 77: VI. RELEVANT LINKS
FIA DR Test website:
https://www.fia.org/events/2021-fia-disaster-recovery-exercise
FIA DR Test registration:
https://portal.fia.org/meetings/individualregistration.aspx?ID=4765 (NEW registration)
https://secure.fia.org/bcp/test-registration.asp (EDIT registration)
Exchange/Clearinghouse Contacts:
https://www.fia.org/sites/default/files/2021-07/FIA_DR_Test_Contacts_2021_0716.xlsx
Exchange/Clearinghouse Test Scripts:
https://www.fia.org/events/2021-fia-disaster-recovery-exercise

## Slide 78: VII. REMAINING SCHEDULE
Aug 18 – FIA DR Test briefing/webinar
Aug 28 (Sat) – Pre-test Communications Testing (CME Group MQ)
Sep 11 (Sat) – Pre-Test Communications Testing
Sep 15 – Monthly Participant Call
Sep 18 (Sat) – CME Group MQ Pre-Test
Sep 25 – Pre-Test Communications Testing
Oct 2 – OCC Pre-Test Communications
Oct 13 – Monthly Participant Call
Oct 15 – Test registration closes
Oct 22 (Fri) – All-Hands Call - Day Before the Test
Oct 23 (Sat) – Annual Industry Test Day
Nov 10 – Post-mortem discussions (tentative)
Note: Participant calls occur at 11:00am EDT (10:00am CDT, 4:00pm BST) on select Wednesdays

## Slide 79: QUESTIONS?
Contact Steve Proctor +1.202.772.3010 sproctor@fia.org